## Overview
KiwiShare — Release Test Plan / UAT Checklist (v0.2)
1. Test Object
Branch under test | pre @ <fill commit hash before starting>
Build / date | <fill: e.g. iOS simulator build 2026-09-xx>
Strategy reference | docs/testing-strategy/testing-strategy.md (v0.1) — this workbook is the release/UAT checklist it calls for
Compatibility targets | Android 7.0+ and iOS 13+ (team decision, meeting minutes 25 Aug)
Backend under test | Render deployment + MongoDB; local integration via `pnpm dev:local`, device via `pnpm dev:device`
Out of scope this round | Payment flow (server model only, no routes), Google sign-in (code wired but excluded by team decision 2026-09-16), user blocking. Do NOT raise defects for these.
2. How to Fill
Status | Pick from dropdown: Not run / Pass / Fail / Blocked. Every case must end as Pass, or have a Defect ID logged in the Defect Log sheet.
Tester / Date | The person who actually executed the case (may differ from Owner).
Evidence | Link to screenshot / screen recording (GitHub issue, Drive, or wiki). Mandatory for all UI cases per team PR rules.
Defect ID | If Fail/Blocked, raise a row in the Defect Log sheet and put its ID here.
3. Status & Priority Legend
Not run | Not executed yet (default).
Pass | Actual result matches expected result.
Fail | Behaviour deviates from expected — log a defect.
Blocked | Cannot execute (dependent case failing, environment broken) — say why in Notes.
P0 | Core marketplace journey; blocks release if failing.
P1 | Important feature; release blocker only if no workaround.
P2 | Polish / robustness; fix or defer by team call.
S1–S4 (defect severity) | S1 crash / data loss — blocks release. S2 major feature broken, no workaround. S3 minor, workaround exists. S4 cosmetic.
4. Owners (adjust names in Test Cases sheet if needed)
Jenny | Authentication & account security, Profile; iPhone real-device regression (own module)
Sam | Watchlist & notifications, API/backend smoke; iPhone real-device regression (own module)
Jack | Publish item flow (incl. GPS/location), Trade; iPhone real-device regression (own module)
Rui | Home / browse / search / item detail, Reports & safety, Web smoke, coordination; iPhone real-device regression (own module)
Jaeger | Chat (text/photo/voice); Android real-device regression (own module)
5. Device Matrix
iPhone testers | Jenny — iPhone 17; Jack — iPhone 16 Pro, iOS 26.6.2; Luna — iPhone 15; Sam — iPhone (model not recorded); Rui — iPhone (model not recorded). Own-module simulator/emulator testing plus physical-iPhone regression.
Jaeger | Samsung physical Android phone (model and Android version not recorded); own-module emulator testing plus physical-Android regression.
All | Dark mode + offline + permission-denied sweep inside your own module (Round 2)
6. Suggested Schedule
Round 1 — Functional | Thu 9/17 – Sat 9/19: each owner executes all cases in their own module (P0 first).
Round 2 — Cross-cutting | Sun 9/20 – Mon 9/21: dark mode / offline / empty / permission states; real-device P0 regression (iPhone: Jenny/Jack/Rui/Sam, Android: Jaeger).
Round 3 — Regression & sign-off | Tue 9/22 before the weekly meeting: re-test all Failed/Blocked, full P0 regression, UAT sign-off at the meeting.
7. Entry / Exit Criteria
Entry | Test accounts + seed data ready by Wed 9/16 evening (see Test Data sheet); latest build installed on all devices in the matrix.
Exit | 100% P0 Pass; P1 Pass or accepted deferral; zero open S1/S2 defects; all evidence linked.
8. Consolidated Test Results | As of 2026-10-02
Total test cases | 70
Executed | 70
Passed | 70
Failed | 0
Blocked | 0
Execution rate | 100%
Pass rate (executed cases) | 100%
Latest update | All 70 planned cases were executed and currently pass after confirmation and retesting with the assigned team members.
Evidence status | 54/70 cases reference evidence (P0 17/19; P1 29/36; P2 8/15). Tester/date metadata is complete; privacy-sensitive screenshots are redacted.
9. Automated Regression Evidence | Local pre-push run on 2026-10-02
Flutter tests | 451 passed; 0 failed
Server Jest | 24 test suites passed; 264 tests passed; 0 failed
Source revision | docs/consolidated-test-evidence based on origin/pre 8bcb615
Web evidence | Web test results are recorded through production smoke evidence and focused Web test output.
10. Multi-round QA & Defect Evidence | GitHub issues created from 2026-09-19
Documented QA rounds | 4 rounds: #279 (09/19), #318 (09/22), #336 (09/23), #355 (09/24)
Individual bug-labelled issues | 45
Closed bug-labelled issues | 42
Open bug-labelled issues | 3
Recorded closure rate | 93.3%
Median resolution time | Approximately 3.42 days
Priority distribution | 21 Urgent; 12 High; 9 Medium; 3 Low
Classification note | The 3 open bug-labelled items concern presentation preparation, security evidence review, and dependency maintenance rather than confirmed product defects.

## Test Data & Setup
Test Data & Environment Setup — do this BEFORE Round 1
1. Test Accounts (register all three via the app, before any testing)
Account A — buyer | Register with a real inbox you can open, e.g. gmail alias yourname+ksa@gmail.com. Browses, watches, buys, reports.
Account B — seller | yourname+ksb@gmail.com. Publishes seed items, chats, changes prices, completes trades.
Account C — fresh | yourname+ksc@gmail.com. Stays empty: first-run empty states and no-avatar placeholder cases.
Why real inboxes | OTP / password-reset emails must actually arrive; gmail aliases all land in one inbox. Each teammate uses their OWN aliases — do not share accounts during testing.
2. Seed Data Checklist (mostly on accounts A & B)
Items | B publishes 3 items with photos (different categories; one high price, one cheap) — feeds browse/detail/watchlist/trade cases.
Watchlist | A watches one of B's items — feeds the price-change notification case.
Conversation | A and B exchange a few messages — feeds chat list / unread badge cases.
Report | A reports one of B's items — feeds the report-history case in Profile.
Trade | A and B agree one trade — feeds QR verification, cancel and rating cases.
Reset-token prep | Know each account's password so forgot-password/change-password cases can be repeated cleanly.
3. Environment
Builds | Latest `pre` branch build everywhere; record branch + commit hash in Overview. Simulators/emulators: everyone. Physical devices: Jenny — iPhone 17; Jack — iPhone 16 Pro (iOS 26.6.2); Luna — iPhone 15; Sam and Rui — iPhone (model not recorded); Jaeger — Samsung Android phone (model/version not recorded).
Backend | Default: Render deployment (health-check it first, see API cases). Local integration: `pnpm dev:local`; physical device against local backend: `pnpm dev:device`.
Toggles | Dark mode: system settings. Offline: airplane mode. Permissions: device Settings > KiwiShare.
API tooling | curl or Postman. Auth token: copy the Authorization header from a logged-in session (dev tools / proxy). Endpoint paths: docs/api-spec.md.
4. Evidence
Where to put | Screenshots / screen recordings attached to a GitHub issue (or PR); paste the link into the Evidence column of the executed case. Mandatory for UI cases.

## Test Cases
Case ID | Module | Scenario | Steps | Expected Result | Priority | Type | Platform | Round | Owner | Status | Tester | Date | Evidence | Defect ID | Notes
KS-T-001 | Auth | Register with email/password | 1. Sign up with a new email/password 2. Complete any verification | Account created, logged in, profile with default displayName | P0 | Functional | iOS+Android | 1 | Jenny | Pass | Jenny; Rui / Sam | 2026-09-19 | Embedded IMG-15 in Evidence Screenshots Physical-iPhone sequence shows the empty form, privacy-redacted valid registration inputs, and the resulting signed-in Profile with the new display name. |  | Also passed by Rui / Sam on 2026-09-19 (Chinese test plan).
KS-T-002 | Auth | Login with valid credentials | 1. Log out if needed 2. Log in with existing account | Home screen loads with user session | P0 | Functional | iOS+Android | 1 | Jenny | Pass | Jenny; Rui / Sam | 2026-09-19 | Embedded IMG-14 in Evidence Screenshots Physical-iPhone evidence shows the authenticated Home screen loaded successfully. |  | Also passed by Rui / Sam on 2026-09-19 (Chinese test plan).
KS-T-003 | Auth | Login with wrong password | 1. Enter valid email + wrong password 2. Submit | Clear error message; no crash; stays on login | P1 | Error state | iOS+Android | 1 | Jenny | Pass | Jenny; Rui / Sam | 2026-09-19 | Embedded IMG-16 in Evidence Screenshots Privacy-redacted physical-iPhone evidence shows invalid credentials rejected with a clear error. |  | Also passed by Rui / Sam on 2026-09-19 (Chinese test plan).
KS-T-004 | Auth | Login with unregistered email | 1. Enter email never registered 2. Submit | Generic error, no user-enumeration hint | P2 | Security | iOS+Android | 1 | Jenny | Pass | Jenny; Rui / Sam | 2026-09-19 |  |  | Also passed by Rui / Sam on 2026-09-19 (Chinese test plan).
KS-T-005 | Auth | Forgot password — request OTP | 1. Use a real inbox you can open (gmail alias, see Test Data sheet) 2. Tap Forgot password, enter that email, submit 3. Check inbox for the OTP 4. Re-request within the cooldown window | OTP email received; re-request within cooldown is rejected with countdown | P0 | Functional | iOS+Android | 1 | Jenny | Pass | Jenny (emulator); Rui / Sam | 2026-09-19 | Embedded IMG-17 in Evidence Screenshots Privacy-redacted physical-iPhone sequence shows reset entry, email delivery, a one-time code and resend countdown. |  | Retested as Pass in the updated test plan. Historical screenshot removed because it contained personal information. Replacement evidence and retest metadata are pending.
KS-T-006 | Auth | Forgot password — wrong / expired OTP | 1. Request OTP 2. Enter wrong code 3. Then enter expired code | Both rejected with clear error; no crash | P1 | Error state | iOS+Android | 1 | Jenny | Pass | Jenny | 2026-09-20 | Embedded IMG-25 in Evidence Screenshots Physical-iPhone sequence shows OTP delivery, invalid or expired OTP rejection, and resend countdown.
KS-T-007 | Auth | Reset password completes | 1. Complete forgot-password with valid OTP 2. Set new password 3. Log in with new; try old | New password works, old password rejected | P0 | Functional | iOS+Android | 1 | Jenny | Pass | Jenny | 2026-09-20 | Screenshot attached in PR #309 https://github.com/UOA-CS734-S2-2026/project-implementation-five-guys/pull/309 Reference only; attachment not downloaded or visually verified.
KS-T-008 | Auth | Change password from profile | 1. Profile > Account > Change password 2. Provide current + new password | Success feedback; next login requires new password | P1 | Functional | iOS+Android | 1 | Jenny | Pass | Jenny | 2026-09-20 | Screenshot attached in PR #239 https://github.com/UOA-CS734-S2-2026/project-implementation-five-guys/pull/239 Reference only; attachment not downloaded or visually verified. | KS-B-003 | KS-B-003 ¦ KS-T-008 ¦ Profile ¦ Change-password dialog: floating labels overlap the field above (no spacing between the three TextFormFields) ¦ Profile > Change password, observe dialog ¦ S4 Cosmetic ¦ Jenny ¦ Jenny ¦ Open ¦ ¦ Add SizedBox(height:16) between fields
KS-T-009 | Auth | Logout & session invalidation | 1. Log out 2. Attempt to open protected screens 3. Relaunch app | Returns to login; protected content inaccessible; session stays logged out | P1 | Security | iOS+Android | 1 | Jenny | Pass | Jenny | 2026-09-20 | Embedded IMG-26 in Evidence Screenshots Physical-iPhone screenshots show signed-out Chat and Watchlist screens requiring authentication.
KS-T-010 | Profile | Profile shows identity data | 1. Open Profile with a user that has avatar + items | Avatar, displayName, trust score, verified badge correct | P1 | Functional | iOS+Android | 1 | Jenny | Pass | Jenny; Rui / Sam | 2026-09-19 | Embedded IMG-03 in Evidence Screenshots Source PR #391. |  | Also passed by Rui / Sam on 2026-09-19 (Chinese test plan).
KS-T-011 | Profile | Edit avatar (R2 upload) | 1. Tap avatar 2. Pick image from gallery/camera | New avatar uploads and shows in Profile, item cards and chat header | P1 | Functional | iOS+Android | 1 | Jenny | Pass | Jenny | 2026-09-20 | Embedded IMG-11 in Evidence Screenshots Source PR #329.
KS-T-012 | Profile | Edit nickname (displayName) | 1. Account > Edit nickname 2. Enter 2–30 chars 3. Save | New name reflected on Profile, item cards and chat conversations | P1 | Functional | iOS+Android | 1 | Jenny | Pass | Jenny; Rui / Sam | 2026-09-19 | Screenshot attached in PR #239 https://github.com/UOA-CS734-S2-2026/project-implementation-five-guys/pull/239 Reference only; attachment not downloaded or visually verified. |  | Also passed by Rui / Sam on 2026-09-19 (Chinese test plan).
KS-T-013 | Profile | Nickname validation | 1. Enter 1-char name 2. Enter 30+ chars | Both rejected with validation message | P2 | Error state | iOS+Android | 1 | Jenny | Pass | Jenny | 2026-09-20 | Screenshot attached in PR #309 https://github.com/UOA-CS734-S2-2026/project-implementation-five-guys/pull/309 Reference only; attachment not downloaded or visually verified. | KS-B-002 | KS-B-002 ¦ KS-T-013 ¦ Profile ¦ Registration accepts displayName >30 chars; edit dialog silently truncates to 30 (inconsistent length limits across entry points) ¦ Register with a 32-char nickname, then edit nickname in Profile and type a 33rd char ¦ S3 Minor ¦ Jenny ¦ Jenny ¦ Open ¦ ¦ Server /auth/register lacks the 2-30 length check that PUT /users has (users.ts:59); client edit uses maxLength:30
KS-T-014 | Profile | No-avatar placeholder | 1. Use account without avatar | Initials placeholder shown, no broken image | P2 | Empty state | iOS+Android | 1 | Jenny | Pass | Rui / Sam | 2026-09-19 | Embedded IMG-11 in Evidence Screenshots Source PR #329. |  | Imported from the Chinese test plan completed by Rui / Sam on 2026-09-19.
KS-T-015 | Profile | Watchlist tab in profile | 1. Open Profile > Watchlist with saved items 2. With an account that has none | Saved items listed; empty state message when none | P1 | Functional | iOS+Android | 1 | Jenny | Pass | Jenny; Rui / Sam | 2026-09-19 | Embedded IMG-07 in Evidence Screenshots Source PR #374. |  | Also passed by Rui / Sam on 2026-09-19 (Chinese test plan).
KS-T-016 | Profile | Report history (Safety & support) | 1. Report an item (see KS-T-053) 2. Open Profile > Safety & support > Report history | The report appears with status and date | P1 | Functional | iOS+Android | 1 | Jenny | Pass | Jenny; Rui / Sam | 2026-09-19 | Screenshot attached in PR #248 https://github.com/UOA-CS734-S2-2026/project-implementation-five-guys/pull/248 Reference only; attachment not downloaded or visually verified. |  | Also passed by Rui / Sam on 2026-09-19 (Chinese test plan).
KS-T-017 | Publish | Publish item end-to-end | 1. Tap Publish 2. Complete all steps: photos, title, desc, price, category, location 3. Submit | Item live and visible in home feed and own profile | P0 | Functional | iOS+Android | 1 | Jack | Pass | Rui / Sam | 2026-09-19 | Embedded IMG-18 in Evidence Screenshots Physical-iPhone listing flow, publish confirmation and own Selling-list visibility. |  | Imported from the Chinese test plan completed by Rui / Sam on 2026-09-19.
KS-T-018 | Publish | Photo upload via R2 | 1. Add 1–5 photos from gallery 2. Add via camera | Photos upload, thumbnails shown in step list and on the item | P0 | Functional | iOS+Android | 1 | Jack | Pass | Jenny | 2026-09-29 | Embedded IMG-18 in Evidence Screenshots Physical-iPhone evidence shows five uploaded photos and rendered thumbnails.
KS-T-019 | Publish | Photo upload failure handling | 1. Start upload 2. Enable airplane mode mid-upload | Controlled error with retry; no orphan/corrupt item | P1 | Error state | iOS+Android | 1 | Jack | Pass | Jack | 2026-09-19
KS-T-020 | Publish | AI-assisted description | 1. Enter title/photos 2. Request AI description 3. Accept suggestion | Sensible description inserted; editable before submit | P2 | Functional | iOS+Android | 1 | Jack | Pass | Rui / Sam | 2026-09-19 | Screenshot attached in PR #277 https://github.com/UOA-CS734-S2-2026/project-implementation-five-guys/pull/277 Reference only; attachment not downloaded or visually verified. |  | Fail by Rui / Sam on 2026-09-19 first time test; retest pass
KS-T-021 | Publish | Missing required fields | 1. Submit publish form with empty title / price / category | Validation blocks with per-field messages; nothing created | P1 | Error state | iOS+Android | 1 | Jack | Pass | Rui / Sam | 2026-09-19 | Embedded IMG-21 in Evidence Screenshots Physical-iPhone evidence shows title, category and price validation errors blocking an incomplete listing. |  | Imported from the Chinese test plan completed by Rui / Sam on 2026-09-19.
KS-T-022 | Publish | GPS location on publish | 1. Grant location permission 2. Publish with current location 3. Deny permission and publish | Nearby location attached when granted; graceful fallback when denied | P1 | Permission | iOS+Android | 1 | Jack | Pass | Jenny | 2026-09-29
KS-T-023 | Publish | Edit / mark sold / delete item | 1. Edit own item price 2. Mark sold 3. Delete item | Edits visible; sold state shown; deleted item gone from browse | P1 | Functional | iOS+Android | 1 | Jack | Pass | Rui / Sam | 2026-09-19 | Embedded IMG-23 in Evidence Screenshots Physical-iPhone evidence shows the item marked SOLD and unavailable. |  | Fail by Rui / Sam on 2026-09-19 first time test; retest pass
KS-T-024 | Discovery | Home feed & refresh | 1. Open Home 2. Pull to refresh | Items load with images and prices; refresh updates list | P0 | Functional | iOS+Android | 1 | Rui | Pass | Rui / Sam | 2026-09-19 | Embedded IMG-01 and IMG-14 in Evidence Screenshots Source PR #391 and physical-iPhone Home feed evidence. |  | Imported from the Chinese test plan completed by Rui / Sam on 2026-09-19.
KS-T-025 | Discovery | Category navigation | 1. Tap each category button | Filtered list per category; active state shown | P1 | Functional | iOS+Android | 1 | Rui | Pass | Rui / Sam | 2026-09-19 |  |  | Imported from the Chinese test plan completed by Rui / Sam on 2026-09-19.
KS-T-026 | Discovery | Keyword search | 1. Search existing item title keyword 2. Search nonsense string | Matches returned; no-results empty state for nonsense | P0 | Functional | iOS+Android | 1 | Rui | Pass | Rui / Sam | 2026-09-19 | Embedded IMG-19 in Evidence Screenshots Physical-iPhone sequence shows matching search results and a clear no-match empty state. |  | Imported from the Chinese test plan completed by Rui / Sam on 2026-09-19.
KS-T-027 | Discovery | Filters | 1. Apply price range / category / condition filters | Results match filter criteria | P1 | Functional | iOS+Android | 1 | Rui | Pass | Jenny | 2026-10-02 | Screenshot attached in PR #325 https://github.com/UOA-CS734-S2-2026/project-implementation-five-guys/pull/325 Reference only; attachment not downloaded or visually verified.
KS-T-028 | Discovery | Sorting | 1. Sort by price asc/desc and newest | Order matches selected sort | P1 | Functional | iOS+Android | 1 | Rui | Pass | Rui / Sam | 2026-09-19 | Embedded IMG-13 in Evidence Screenshots Physical-iPhone sort and filter evidence.
KS-T-029 | Discovery | Offline browse | 1. Enable airplane mode 2. Open Home / search | Controlled error/empty state with retry; no crash | P1 | Offline | iOS+Android | 2 | Rui | Pass | Rui / Sam | 2026-09-19 | Embedded IMG-24 in Evidence Screenshots Physical-iPhone airplane-mode evidence shows clear loading errors and Retry actions.
KS-T-030 | Item detail | Item detail content | 1. Open any item | All photos, description, price, seller name/avatar, location shown | P0 | Functional | iOS+Android | 1 | Rui | Pass | Rui / Sam | 2026-09-19 | Screenshot attached in PR #181 https://github.com/UOA-CS734-S2-2026/project-implementation-five-guys/pull/181 Reference only; attachment not downloaded or visually verified. |  | Imported from the Chinese test plan completed by Rui / Sam on 2026-09-19.
KS-T-031 | Item detail | Seller identity on detail | 1. Change own nickname (KS-T-013) 2. Open own item detail | Updated displayName shown on detail and seller section | P2 | Functional | iOS+Android | 2 | Rui | Pass | Rui / Sam | 2026-09-19 | Embedded IMG-27 in Evidence Screenshots Production item detail shows seller name, profile image, verification status and trust score. See docs/testing-evidence/2026-10-03-additional-release-evidence.md. |  | Fail by Rui / Sam on 2026-09-19 first time test; retest pass
KS-T-032 | Watchlist | Add / remove watchlist item | 1. Tap heart on item detail 2. Check profile Watchlist 3. Remove it | State toggles; list updates; heart state persists after app restart | P1 | Functional | iOS+Android | 1 | Sam | Pass | Rui / Sam | 2026-09-19 | Screenshot attached in PR #372 https://github.com/UOA-CS734-S2-2026/project-implementation-five-guys/pull/372 Reference only; attachment not downloaded or visually verified. |  | Imported from the Chinese test plan completed by Rui / Sam on 2026-09-19.
KS-T-033 | Watchlist | Price-change notification | Setup: A watches an item owned by B (two devices) 1. A taps heart on B's item 2. B edits that item's price 3. Observe A's device | A receives price-change notification (push or in-app) | P1 | Functional | iOS+Android | 2 | Sam | Pass | Rui / Sam | 2026-09-19 | Automated evidence: docs/testing-evidence/2026-10-03-additional-release-evidence.md Price-drop notification policy, preferences, quota, idempotency and provider-failure tests passed.
KS-T-034 | Notifications | Permission prompt & denial | 1. Fresh install, trigger first notification 2. Deny permission | App remains usable; no crash; sensible degraded behaviour | P1 | Permission | iOS+Android | 2 | Sam | Pass | Rui / Sam | 2026-09-19 | Screenshot attached in PR #194 https://github.com/UOA-CS734-S2-2026/project-implementation-five-guys/pull/194 Reference only; attachment not downloaded or visually verified.
KS-T-035 | Notifications | Notification routing | Setup: two devices; B sends A a message while A is backgrounded 1. Wait for push on A's device 2. Tap the notification | Opens the related conversation/item screen | P2 | Functional | iOS+Android | 2 | Sam | Pass | Rui / Sam | 2026-09-19
KS-T-036 | Chat | Text chat realtime | Setup: device 1 = account A, device 2 = account B (Test Data sheet) 1. A sends several messages to B 2. B replies while A's app is backgrounded | Messages appear near-instantly; correct order; unread badge on B | P0 | Functional | iOS+Android | 1 | Jaeger | Pass | Rui / Sam | 2026-09-19 | Embedded IMG-12 in Evidence Screenshots Source PR #311. |  | Imported from the Chinese test plan completed by Rui / Sam on 2026-09-19.
KS-T-037 | Chat | Chat entry with item context | 1. Open item detail 2. Tap chat with seller | Conversation opens showing the item card/context | P1 | Functional | iOS+Android | 1 | Jaeger | Pass | Jaeger | 2026-09-29 | Embedded IMG-12 in Evidence Screenshots Source PR #311.
KS-T-038 | Chat | Unread badge behaviour | 1. Receive messages in several conversations 2. Open one | Badge counts correct; opened conversation badge clears | P1 | Functional | iOS+Android | 1 | Jaeger | Pass | Rui / Sam | 2026-09-19 | Embedded IMG-11 in Evidence Screenshots Source PR #329. |  | Imported from the Chinese test plan completed by Rui / Sam on 2026-09-19.
KS-T-039 | Chat | Photo message | 1. Send photo in chat 2. View on receiver | Photo uploads, thumbnails render, full view opens | P1 | Functional | iOS+Android | 1 | Jaeger | Pass | Jaeger | 2026-09-29 | Embedded IMG-22 in Evidence Screenshots Physical-iPhone evidence shows a photo message uploaded and rendered in chat.
KS-T-040 | Chat | Voice message | 1. Record voice message 2. Play on receiver | Records and plays; duration shown; deny-mic path handled | P2 | Functional | iOS+Android | 1 | Jaeger | Pass | Jaeger | 2026-09-29 | Embedded IMG-12 in Evidence Screenshots Source PR #311.
KS-T-041 | Chat | Message sanitisation | 1. Send message containing <script> / HTML / emoji / long text | Rendered as plain text, no injection/broken layout | P1 | Security | iOS+Android | 1 | Jaeger | Pass | Jaeger | 2026-09-29 | Automated evidence: docs/testing-evidence/2026-10-03-additional-release-evidence.md Chat sanitisation and message-moderation tests passed.
KS-T-042 | Chat | Swipe delete conversation | 1. Swipe a conversation 2. Confirm | Conversation removed; reappears on new message | P2 | Functional | iOS+Android | 1 | Jaeger | Pass | Jaeger | 2026-09-29
KS-T-043 | Trade | Initiate trade | 1. From chat/detail, propose trade on an item 2. Other account accepts | Order/trade created with correct item, price and status | P0 | Functional | iOS+Android | 1 | Jack | Pass | Jack | 2026-09-29 | Embedded IMG-02 in Evidence Screenshots Source PR #391.
KS-T-044 | Trade | QR / handshake verification | 1. Both parties meet; complete QR verification flow | Meetup verified; trade marked completed for both | P0 | Functional | iOS+Android | 1 | Jack | Pass | Jack | 2026-09-29 | Embedded IMG-04 in Evidence Screenshots Source PR #391.
KS-T-045 | Trade | Cancel trade | 1. Cancel a pending trade | Status reverts; item available again; both parties notified | P1 | Functional | iOS+Android | 1 | Jack | Pass | Jack | 2026-09-29
KS-T-046 | Trade | Rating after completion | 1. Complete a trade 2. Leave a rating/review | Rating saved and shown on counterparty profile | P2 | Functional | iOS+Android | 2 | Jack | Pass | Jack | 2026-09-29 | Embedded IMG-04 in Evidence Screenshots Source PR #391.
KS-T-047 | Safety | Report item / user | 1. Report an item and a user with reason + description | Confirmation shown; report stored server-side | P1 | Functional | iOS+Android | 1 | Rui | Pass | Rui / Sam | 2026-09-19 | Screenshot attached in PR #317 https://github.com/UOA-CS734-S2-2026/project-implementation-five-guys/pull/317 Reference only; attachment not downloaded or visually verified. |  | Imported from the Chinese test plan completed by Rui / Sam on 2026-09-19.
KS-T-048 | Safety | Duplicate report handling | 1. Report the same item twice | Sensible handling (dedupe or allowed) without error/crash | P2 | Error state | iOS+Android | 2 | Rui | Pass | Rui / Sam | 2026-09-19 | Automated evidence: docs/testing-evidence/2026-10-03-additional-release-evidence.md Duplicate report submissions are rejected without creating another record. |  | Imported from the Chinese test plan completed by Rui / Sam on 2026-09-19.
KS-T-049 | Safety | Unauthorised data access | 1. As normal user, attempt to edit another user's item via UI | Rejected with 401/403; no data change | P1 | Security | API | 2 | Rui | Pass | Rui / Sam | 2026-09-19 |  |  | Imported from the Chinese test plan completed by Rui / Sam on 2026-09-19.
KS-T-050 | API | Backend health on Render | 1. GET deployed API health endpoint 2. Load app against Render backend | Healthy response; app functions against deployed backend | P0 | API | API | 1 | Sam | Pass | Rui / Sam | 2026-09-19 | Live production API evidence: docs/testing-evidence/2026-10-03-additional-release-evidence.md GET /health returned HTTP 200 and OK from Render.
KS-T-051 | API | Unauthenticated access | 1. Call protected endpoints without token (curl/Postman) | 401 returned; no data leak | P0 | Security | API | 1 | Sam | Pass | Rui / Sam | 2026-09-19 | Live production API and automated evidence: docs/testing-evidence/2026-10-03-additional-release-evidence.md GET /api/users/me without a token returned HTTP 401 with a safe error response.
KS-T-052 | API | OTP / reset endpoints abuse | 1. Spam request-password-reset rapidly | Cooldown/429 enforced server-side | P1 | Security | API | 2 | Sam | Pass | Rui / Sam | 2026-09-19 | Automated evidence: docs/testing-evidence/2026-10-03-additional-release-evidence.md OTP rate-limiting tests passed in the isolated server test environment.
KS-T-053 | API | Data persistence | 1. Publish item / send message 2. Restart app & server round-trip | Data persists correctly in MongoDB | P1 | API | API | 1 | Sam | Pass | Rui / Sam | 2026-09-19 | Embedded IMG-20 in Evidence Screenshots Privacy-redacted physical-iPhone evidence shows the published listing with persisted image, title, price and availability.
KS-T-054 | Performance | App cold start time | 1. Force-kill the app 2. Cold start on emulator and real device, timing tap-to-home-interactive 3. Repeat 3x per device | Cold start consistently fast (target < 3 s), no long white screen; record timings in Evidence | P1 | Performance | iOS+Android | 2 | Sam | Pass | Rui / Sam | 2026-09-19
KS-T-055 | Performance | Home feed full-scroll smoothness | 1. Seed 50+ items (Test Data sheet) 2. Scroll the entire home feed on emulator and real device 3. Note any jank / freezes | Scrolling stays smooth; no visible frame drops; note which device was used | P1 | Performance | iOS+Android | 2 | Rui | Pass | Rui / Sam | 2026-09-19
KS-T-056 | Performance | API latency baseline & light load | 1. Measure response time of key GET endpoints (items list, item detail, chat history) 2. Load one endpoint with ~20 concurrent requests for 30 s (autocannon/k6/hey) 3. Record p50/p95 and error count | Zero errors under light load; latency stable and acceptable; record numbers in Evidence | P1 | Performance | API | 3 | Sam | Pass | Rui / Sam | 2026-09-19 | Performance evidence: docs/testing-evidence/api-performance/2026-10-03-render-follow-up.json 80/80 requests succeeded; 0% errors; overall p50 620.01 ms and p95 1407.51 ms.
KS-T-057 | Performance | Item detail image loading | 1. Open a 5-photo item on a real device 2. Repeat on a throttled connection if possible | Thumbnails load progressively; full images open without freeze or memory warning | P2 | Performance | iOS+Android | 2 | Jack | Pass | Jack | 2026-09-29
KS-T-058 | Cross-cutting | Dark mode — auth & profile | 1. Switch system/app to dark mode 2. Walk login, forgot-password, profile screens | Text readable, contrast OK, no white-on-white (recent fix) | P1 | Cross-cutting | iOS+Android | 2 | Jenny | Pass | Jenny | 2026-09-29 | Embedded IMG-06 and IMG-31 in Evidence Screenshots Source PR #374 and Android dark-mode login evidence.
KS-T-059 | Cross-cutting | Dark mode — publish & detail | 1. Dark mode over publish flow and item detail | All controls readable; images unaffected | P1 | Cross-cutting | iOS+Android | 2 | Jack | Pass | Jack | 2026-09-29 | Screenshot attached in PR #265 https://github.com/UOA-CS734-S2-2026/project-implementation-five-guys/pull/265 Reference only; attachment not downloaded or visually verified.
KS-T-060 | Cross-cutting | Dark mode — discovery & reports | 1. Dark mode over home/search/detail/report dialogs | Consistent colors, readable text | P1 | Cross-cutting | iOS+Android | 2 | Rui | Pass | Rui / Sam | 2026-09-19 | Embedded IMG-05 and IMG-31 in Evidence Screenshots Source PR #374 and Android dark-mode marketplace discovery evidence. |  | Fail by Rui / Sam on 2026-09-19 first time test; retest pass
KS-T-061 | Cross-cutting | Dark mode — chat & watchlist | 1. Dark mode over chat list, conversation, watchlist | Consistent colors, readable text | P1 | Cross-cutting | iOS+Android | 2 | Jaeger | Pass | Jaeger | 2026-09-29 | Embedded IMG-07 and IMG-31 in Evidence Screenshots Source PR #374 and Android dark-mode Watchlist error and Retry evidence.
KS-T-062 | Cross-cutting | First-run empty states | 1. Fresh account with no items/chats/watchlist/reports | Friendly empty states everywhere; no blank screens | P2 | Empty state | iOS+Android | 2 | Rui | Pass | Rui / Sam | 2026-09-19
KS-T-063 | Cross-cutting | App resume / background | 1. Background app mid-flow 2. Return after 1 min and 10 min | Session kept or clean re-auth; no state corruption | P2 | Cross-cutting | iOS+Android | 2 | Sam | Pass | Rui / Sam | 2026-09-19
KS-T-064 | Cross-cutting | Fresh install vs upgrade | 1. Fresh install and log in 2. (If applicable) install over existing build | Clean first-run; existing session/data intact on upgrade | P2 | Cross-cutting | iOS+Android | 3 | Sam | Pass | Rui / Sam | 2026-09-19
KS-T-065 | Cross-cutting | Real-device regression — iPhone (Auth & Profile) | 1. Install latest pre build on physical iPhone (iOS 13+) 2. Re-run your module's P0 cases from this sheet on the device 3. Attach evidence | All P0 cases pass on real device | P0 | Cross-cutting | iOS | 2 | Jenny | Pass | Jenny | 2026-09-29 | Embedded IMG-14 in Evidence Screenshots Physical-iPhone authenticated Home evidence.
KS-T-066 | Cross-cutting | Real-device regression — iPhone (Publish & Trade) | 1. Install latest pre build on physical iPhone (iOS 13+) 2. Re-run your module's P0 cases on the device 3. Attach evidence | All P0 cases pass on real device | P0 | Cross-cutting | iOS | 2 | Jack | Pass | Jack | 2026-09-29
KS-T-067 | Cross-cutting | Real-device regression — iPhone (Discovery & Safety) | 1. Install latest pre build on physical iPhone (iOS 13+) 2. Re-run your module's P0 cases on the device 3. Attach evidence | All P0 cases pass on real device | P0 | Cross-cutting | iOS | 2 | Rui | Pass | Rui / Sam | 2026-09-19 | Embedded IMG-28 and IMG-29 in Evidence Screenshots Rui's evidence covers physical-iPhone order and trade states, iPhone reporting and seller identity, and Android reports, profile and marketplace discovery.
KS-T-068 | Cross-cutting | Real-device regression — iPhone (Watchlist & Notifications) | 1. Install latest pre build on physical iPhone (iOS 13+) 2. Re-run your module's P0 cases on the device 3. Attach evidence | All P0 cases pass on real device | P0 | Cross-cutting | iOS | 2 | Sam | Pass | Rui / Sam | 2026-09-19 | Embedded IMG-30 in Evidence Screenshots Sam physical-iPhone evidence shows an authenticated own-listing detail page and the owner watchlist restriction.
KS-T-069 | Cross-cutting | Real-device regression — Android (Chat) | 1. Install latest pre build on physical Android (7.0+) 2. Re-run your module's P0 cases on the device 3. Attach evidence | All P0 cases pass on real device | P0 | Cross-cutting | Android | 2 | Jaeger | Pass | Jaeger | 2026-09-29
KS-T-070 | Web | Web app smoke | 1. Open web client in Chrome 2. Log in, browse, open an item | Core flows work; no console errors blocking use | P2 | Functional | Web | 3 | Rui | Pass | Rui / Sam | 2026-09-19 | Embedded IMG-27 in Evidence Screenshots Production Web login, marketplace and item-detail smoke passed. See docs/testing-evidence/2026-10-03-additional-release-evidence.md.

## Defect Log
Defect ID | Related Case | Module | Summary | Steps to Reproduce | Severity | Reported By | Assigned To | Status | Date | Notes
KS-B-001 (example) | KS-T-007 | Auth | Expired OTP shows raw server error | 1. Request OTP 2. Wait 10 min 3. Enter code | S3 Minor | Jenny | Jenny | Closed |  | Replace with friendly message
KS-B-002 | KS-T-013 | Profile | Registration accepted display names longer than 30 characters while Profile editing capped them at 30. | Register with a 32-character nickname, then edit the nickname in Profile and enter a 33rd character. | S3 Minor | Jenny | Jenny | Closed | 2026-09-16 | Fixed in PR #309 by applying the 2-30 character limit consistently; the linked test case now passes.
KS-B-003 | KS-T-008 | Profile | Floating labels overlapped adjacent fields in the change-password dialog. | Open Profile > Change password and inspect spacing between the three password fields. | S4 Cosmetic | Jenny | Jenny | Closed | 2026-09-16 | Fixed in PR #309 by restoring spacing between fields; the linked test case now passes.

## Evidence Screenshots
Evidence ID | Related cases | Source PR / asset | Coverage and limits | Screenshot
IMG-01 | KS-T-024 | PR #391 docs/assets/readme/home-marketplace.jpg Source commit f55fc4e https://github.com/UOA-CS734-S2-2026/project-implementation-five-guys/blob/f55fc4e066bc7a755a55907dd4f29797d0805c7f/docs/assets/readme/home-marketplace.jpg | Marketplace images and prices are visible.
IMG-02 | KS-T-043 | PR #391 docs/assets/readme/meetup-awaiting-payment.jpg Source commit f55fc4e https://github.com/UOA-CS734-S2-2026/project-implementation-five-guys/blob/f55fc4e066bc7a755a55907dd4f29797d0805c7f/docs/assets/readme/meetup-awaiting-payment.jpg | Item context and scheduled meetup awaiting payment are visible.
IMG-03 | KS-T-010 | PR #391 docs/assets/readme/profile-trust.jpg Source commit f55fc4e https://github.com/UOA-CS734-S2-2026/project-implementation-five-guys/blob/f55fc4e066bc7a755a55907dd4f29797d0805c7f/docs/assets/readme/profile-trust.jpg | Profile avatar, username, trust score and badges are visible.
IMG-04 | KS-T-044, KS-T-046 | PR #391 docs/assets/readme/transaction-completed.jpg Source commit f55fc4e https://github.com/UOA-CS734-S2-2026/project-implementation-five-guys/blob/f55fc4e066bc7a755a55907dd4f29797d0805c7f/docs/assets/readme/transaction-completed.jpg | Completed transaction and released-funds states are visible.
IMG-05 | KS-T-060 | PR #374 docs/dark-mode-home.png Source commit f55fc4e https://github.com/UOA-CS734-S2-2026/project-implementation-five-guys/blob/f55fc4e066bc7a755a55907dd4f29797d0805c7f/docs/dark-mode-home.png | Android emulator dark-mode Home is visible.
IMG-06 | KS-T-058 | PR #374 docs/dark-mode-login-sheet.png Source commit f55fc4e https://github.com/UOA-CS734-S2-2026/project-implementation-five-guys/blob/f55fc4e066bc7a755a55907dd4f29797d0805c7f/docs/dark-mode-login-sheet.png | Android emulator dark-mode login sheet is visible.
IMG-07 | KS-T-015, KS-T-061 | PR #374 docs/dark-mode-watchlist.png Source commit f55fc4e https://github.com/UOA-CS734-S2-2026/project-implementation-five-guys/blob/f55fc4e066bc7a755a55907dd4f29797d0805c7f/docs/dark-mode-watchlist.png | Android emulator dark-mode Watchlist error and Retry state are visible.
IMG-08 | KS-T-024 | PR #371 docs/screenshots/pr-371/compact-product-cards.png Source commit f55fc4e https://github.com/UOA-CS734-S2-2026/project-implementation-five-guys/blob/f55fc4e066bc7a755a55907dd4f29797d0805c7f/docs/screenshots/pr-371/compact-product-cards.png | Compact Home product cards are visible.
IMG-09 | KS-T-024 | PR #371 docs/screenshots/pr-371/home-overview.png Source commit f55fc4e https://github.com/UOA-CS734-S2-2026/project-implementation-five-guys/blob/f55fc4e066bc7a755a55907dd4f29797d0805c7f/docs/screenshots/pr-371/home-overview.png | Home overview is visible.
IMG-10 | KS-T-024 | PR #371 docs/screenshots/pr-371/location-normalization.png Source commit f55fc4e https://github.com/UOA-CS734-S2-2026/project-implementation-five-guys/blob/f55fc4e066bc7a755a55907dd4f29797d0805c7f/docs/screenshots/pr-371/location-normalization.png | Normalised locations on Home cards are visible.
IMG-11 | KS-T-011, KS-T-014, KS-T-038 | PR #329 docs/testing-evidence/issues-301-302/after-chat-participant-avatars.jpg Source commit f55fc4e https://github.com/UOA-CS734-S2-2026/project-implementation-five-guys/blob/f55fc4e066bc7a755a55907dd4f29797d0805c7f/docs/testing-evidence/issues-301-302/after-chat-participant-avatars.jpg | Chat list shows participant photos, fallback initials and unread markers.
IMG-12 | KS-T-036, KS-T-037, KS-T-040 | PR #311 docs/testing-evidence/issues-301-302/after-voice-tap-bar.png Source commit f55fc4e https://github.com/UOA-CS734-S2-2026/project-implementation-five-guys/blob/f55fc4e066bc7a755a55907dd4f29797d0805c7f/docs/testing-evidence/issues-301-302/after-voice-tap-bar.png | Flutter Web voice composer, text messages and item context are visible.
REF-01 | KS-T-007 | PR #309 https://github.com/UOA-CS734-S2-2026/project-implementation-five-guys/pull/309 | OTP password-reset screen is visible. | Screenshot attached in PR description. Attachment not downloaded or visually verified.
REF-02 | KS-T-008 | PR #239 https://github.com/UOA-CS734-S2-2026/project-implementation-five-guys/pull/239 | Change-password screenshot; PR #309 also describes spacing fix. Next-login behaviour is not established by this reference. | Screenshot attached in PR description. Attachment not downloaded or visually verified.
REF-03 | KS-T-012 | PR #239 https://github.com/UOA-CS734-S2-2026/project-implementation-five-guys/pull/239 | Before/after username screenshots. Other screens and latest release retest are not established by this reference. | Screenshot attached in PR description. Attachment not downloaded or visually verified.
REF-04 | KS-T-013 | PR #309 https://github.com/UOA-CS734-S2-2026/project-implementation-five-guys/pull/309 | Screenshot labelled length limit. Attachment not downloaded or visually verified. | Screenshot attached in PR description. Attachment not downloaded or visually verified.
REF-05 | KS-T-016 | PR #248 https://github.com/UOA-CS734-S2-2026/project-implementation-five-guys/pull/248 | Report-history screenshots. PR describes Android emulator verification against real database records. | Screenshot attached in PR description. Attachment not downloaded or visually verified.
REF-06 | KS-T-020 | PR #277 https://github.com/UOA-CS734-S2-2026/project-implementation-five-guys/pull/277 | PR documents AI drafting and includes nine iPhone Simulator screenshots. | Screenshot attached in PR description. Attachment not downloaded or visually verified.
REF-07 | KS-T-027 | PR #325 https://github.com/UOA-CS734-S2-2026/project-implementation-five-guys/pull/325 | Filter-badge fix and screenshot are recorded. | Screenshot attached in PR description. Attachment not downloaded or visually verified.
REF-08 | KS-T-030 | PR #181 https://github.com/UOA-CS734-S2-2026/project-implementation-five-guys/pull/181 | Product-detail reporting entry screenshots are recorded. | Screenshot attached in PR description. Attachment not downloaded or visually verified.
REF-09 | KS-T-032 | PR #372 https://github.com/UOA-CS734-S2-2026/project-implementation-five-guys/pull/372 | Four watchlist-heart screenshots are recorded. | Screenshot attached in PR description. Attachment not downloaded or visually verified.
REF-10 | KS-T-034 | PR #194 https://github.com/UOA-CS734-S2-2026/project-implementation-five-guys/pull/194 | Notification-permission screenshot is recorded. | Screenshot attached in PR description. Attachment not downloaded or visually verified.
REF-11 | KS-T-047 | PR #317 https://github.com/UOA-CS734-S2-2026/project-implementation-five-guys/pull/317 | Contextual report-form screenshot is recorded. | Screenshot attached in PR description. Attachment not downloaded or visually verified.
REF-12 | KS-T-059 | PR #265 https://github.com/UOA-CS734-S2-2026/project-implementation-five-guys/pull/265 | PR documents dark-mode contrast fixes and includes screenshots. | Screenshot attached in PR description. Attachment not downloaded or visually verified.
IMG-13 | KS-T-028 | User-supplied physical iPhone screenshot, 2026-10-03 | Sort/filter controls and selected price range are visible. Final result ordering is not fully established by this screenshot.
IMG-14 | KS-T-002, KS-T-024, KS-T-065 | User-supplied physical iPhone screenshot, 2026-10-03 | Authenticated Home feed and product content visibly load on a physical iPhone.
IMG-15 | KS-T-001 | User-supplied physical iPhone screenshot, privacy-redacted, 2026-10-03 | Three physical-iPhone screenshots show the empty registration form, privacy-redacted valid inputs, and the resulting signed-in Profile with the new display name, establishing successful account creation and login.
IMG-16 | KS-T-003 | User-supplied physical iPhone screenshot, privacy-redacted, 2026-10-03 | Invalid credentials are rejected with a clear error while the login screen remains available.
IMG-17 | KS-T-005 | User-supplied physical iPhone screenshots, privacy-redacted, 2026-10-03 | Sequence shows password-reset entry, email delivery with a one-time code, the reset form and OTP resend countdown.
IMG-18 | KS-T-017, KS-T-018 | User-supplied physical iPhone screenshots, 2026-10-03 | Sequence shows the listing form, five uploaded photos, completed listing fields, live-success confirmation and the item in the owner's Selling list.
IMG-19 | KS-T-026 | User-supplied physical iPhone screenshots, 2026-10-03 | Sequence shows a search term, a matching product result and a no-match empty state.
IMG-20 | KS-T-053 | User-supplied physical iPhone screenshot, privacy-redacted, 2026-10-03 | Published listing shows its image set, title, price, availability and owner context after reload.
IMG-21 | KS-T-021 | User-supplied physical iPhone screenshot, 2026-10-03 | Required-field validation is visible for title, category and price, showing submission is blocked.
IMG-22 | KS-T-039 | User-supplied physical iPhone screenshot, 2026-10-03 | Photo message is uploaded and rendered in the chat conversation on a physical iPhone.
IMG-23 | KS-T-023 | User-supplied physical iPhone screenshot, 2026-10-03 | Item is visibly marked SOLD and unavailable on a physical iPhone.
IMG-24 | KS-T-029 | User-supplied physical iPhone screenshot, 2026-10-03 | Airplane mode and clear category and product loading errors with Retry actions are visible.
IMG-25 | KS-T-009 | User-supplied physical iPhone screenshot, 2026-10-03 | logout current user, then check the protected pages
IMG-25 | KS-T-006 | Team-supplied physical iPhone screenshots, privacy-redacted, 2026-10-03 | OTP email, invalid or expired OTP rejection, and resend countdown are visible.
IMG-26 | KS-T-009 | Team-supplied physical iPhone screenshots, 2026-10-03 | Signed-out Chat and Watchlist screens require authentication before protected content is displayed.
IMG-27 | KS-T-031; KS-T-070 | Production web smoke screenshots, 2026-10-03 | Production login, marketplace and item-detail pages load successfully; seller identity, verification and trust score are visible on item detail.
IMG-28 | KS-T-067 | Rui physical-iPhone test photographs, 2026-10-03 | Physical iPhone evidence shows authenticated order history, multiple payment and meetup states, invoice, QR handover, chat, trade location and an in-progress paid order.
IMG-29 | KS-T-067 | Rui team-supplied iPhone and Android test evidence, 2026-10-03 | Evidence shows listing reporting, public seller identity and sold-item state on iPhone, plus submitted safety reports, authenticated profile and marketplace discovery on Android.
IMG-30 | KS-T-068 | Sam physical-iPhone test screenshot, 2026-10-03 | Physical-iPhone evidence shows an authenticated own-listing detail page, verified seller identity, watchlist protection for the owner's item, edit access and the disabled owner-chat state.
IMG-31 | KS-T-058; KS-T-060; KS-T-061 | Team-supplied Android dark-mode screenshots, 2026-10-03 | Android dark-mode evidence shows readable login controls, marketplace discovery content, navigation and a clear Watchlist error with Retry action.